# Terms of Reference (TOR)

Hiring of Social Media Agency for HPV Vaccine Awareness Campaign
Rahnuma-FPAP / GAVI / Oxford Policy Management (OPM)

## 1. Background

Rahnuma-FPAP, in partnership with GAVI Alliance and Oxford Policy Management (OPM), is implementing the Accelerated HPV Vaccine Social Media Campaign to raise awareness, promote vaccination, counter misinformation, and mobilize parents/caregivers across Pakistan.

This campaign follows the Accelerated HPV Vaccine Social Media Campaign Plan (Dec 1 Jan 15, 2025) and will run across:

- Facebook

- Instagram

- YouTube

- TikTok

- WhatsApp

- LinkedIn

- Twitter (X)

A specialized social media agency is required to execute the campaign professionally within the approved budget.

## 2. Purpose of the Assignment

To hire a digital media agency to plan, design, boost, manage, and deliver a high-impact HPV vaccine awareness campaign across all official social media platforms.

## 3. Scope of Work

### A. Content Creation & Design

The agency will create platform-optimized content for all channels :

- 15 graphics/infographics

- 8–10 myth-buster short videos

- 12 TikTok/Instagram reels

- 5 long expert video

- 5 YouTube ad creatives

- 6 WhatsApp shareables

- Twitter/X-optimized visuals, short clips, and text posts

Twitter/X-specific content includes:

- Short informative threads

- Real-time campaign updates

- Quick expert quotes

- Engagement posts (polls, Q&A highlights)

### B. Social Media Management

Daily handling of all campaign platforms including:

- Facebook

- Instagram

- YouTube

- TikTok

- Twitter (X)

- LinkedIn

- WhatsApp broadcast dissemination

Responsibilities:

- Daily scheduling & posting

- Responding to comments & inbox queries

- Monitoring and countering misinformation

- Sentiment analysis

- Escalation of sensitive/health-related queries

Twitter-specific tasks:

- Daily tweets/threads

- Responding to public questions

- Tracking conversations & trends

- Rapid counter-misinformation responses

### C. Paid Media Management

(Allocated strategically across all platforms based on campaign needs)

Boosting coverage includes:

- Facebook Ads

- Instagram Ads

- YouTube Ads

- TikTok Ads

- Selective Twitter (X) boosts as required

Agency duties:

- Ad planning & setup

- Target audience selection (parents, caregivers, guardians)

- Weekly optimization

- Weekly campaign analytics reporting

### D. Campaign Phasing (per provided plan)

| #### Phase 1 — Celebrate & Validate (Dec 1–15) | - Success stories (#GirlsVaccinated) - Testimonials - Progress announcement threads on Twitter |
| --- | --- |
| #### Phase 2 — Trust & Debunk (Dec 15–31) | - Myth-buster videos - Expert Q&A content - Priority for boosting - Twitter debunking responses & threads |
| #### Phase 3 — Action & Routine (Dec 31–Jan 15 ) | - Clinic posts & vaccination reminders - Final messaging - Twitter quick facts & reminders |

### E. Performance Tracking & Reporting

Weekly reports will include:

- Platform-wise metrics

- Twitter (X) analytics (impressions, engagement, retweets)

- Paid media performance

- Audience insights

- Sentiment analysis

- Recommendations

Overall KPIs:

- Reach: 4,500,000+

- Engagement: 250,000+

- Video Views: 1,500,000+

- Sentiment improvement: 15%

## 4. Deliverables

| ### Content Deliverables | - 15 infographics - 8–10 short videos - 12 reels - 5 expert video - 5 YouTube ad creatives - 6 WhatsApp shareables - Twitter/X content package (threads, visuals, clips) |
| --- | --- |
| ### Management Deliverables | - Weekly posting calendar - Daily platform monitoring - Real-time Twitter engagement - Weekly reports |
| ### Final Deliverables | - Final campaign report - Complete content archive - Boosting analytics summary |

## 5. Duration

- Start: Upon signing of the contract.

- 45 Days
December 1 – January 15. 2025
(Extendable for future phases)

## 6. Required Agency Expertise

- 3+ years digital marketing experience

- Proven multi-platform campaign experience

- Skilled design & video editing team

- Health campaign experience (preferred)

- Expertise in:

  - Meta Ads

  - YouTube/Google Ads

  - TikTok Ads

  - Twitter (X) engagement & advertising

  - Linkedin Ads

- Strong community management

## 7. Responsibilities of Rahnuma-FPAP / GAVI / OPM

- Provide branding guidelines

- Provide expert-reviewed content

- Facilitate district-level coordination

- Provide boosting budget

- Review and approve outputs

## 8. Responsibilities of the Agency

- Deliver content that aligns with key messages

- Ensure accuracy of health information

- Maintain professional public communication

- Manage and protect campaign data

- Provide timely posting, reporting, and moderation

Payment Terms

Payment Schedule:

100% on completion of assignment and satisfactory submission of Socialmedia Campaign  report as final deliverable approved by Rahnuma-FPAP. Payment will be made through cross-cheque. Tax will be deducted as per laws of Government of Pakistan.

Liaison Persons from Rahnuma-FPAP: Ayfar Khan Communication Manager, Rahnuma-FPAP 3-A Temple Road, Lahore-Pakistan Phone No: (042) 111 22 33 66, Ext 324 E-mail address: Rahnuma.Communications@fpapak.org

## 10. Proposal Submission Requirements

Agencies must submit:

- Company profile

- Portfolio of similar campaigns

- Technical approach

- Workplan

- Team structure including Twitter/X specialists

- Previous performance evidence

- Submission date of proposal is 28 Nov 2025.